## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
US01 | TA Profile Creation | As a TA, I want to create a profile, so that I can showcase my skills to the school. | High | 1 | 1. Can input Name, ID, and Skills. 2. Data is saved to a local JSON/CSV file. | 5 | Must use file I/O, no DB. | 2026-03-06 | 2026-03-12
US02 | Job Posting (MO) | As a Module Organiser, I want to post TA job requirements, so that students can apply. | High | 1 | 1. Can set Module Name and duties. 2. Job details are persisted in text format. | 5 | Core functionality for MO. | 2026-03-06 | 2026-03-15
US03 | Job Browsing | As a TA, I want to browse available jobs, so that I can find suitable positions. | High | 2 | 1. Display a list of all active job posts. 2. Can view details for each job. | 3 | Needs to read from the job file. | 2026-03-23 | 2026-03-28
US04 | Application Submission | As a TA, I want to apply for a specific job, so that I can be considered for the role. | High | 2 | 1. Link TA ID with Job ID. 2. Prevent duplicate applications for one job. | 3 | Update application record file. | 2026-03-29 | 2026-04-05
US05 | Applicant Selection | As a MO, I want to select a TA from the applicants, so that I can fill the position. | High | 3 | 1. MO can view all applicants for their job. 2. Can change status to 'Selected' or 'Rejected'. | 5 | Update global status file. | 2026-04-13 | 2026-04-20
US06 | Workload Monitoring | As an Admin, I want to check TA's overall workload, so that I can ensure balanced allocation. | Medium | 3 | 1. Show total number of jobs per TA. 2. Highlight TAs with excessive workload. | 5 | Requires cross-referencing files. | 2026-04-21 | 2026-05-01
US07 | AI Skill Matching | As a MO, I want AI to match TA skills with job requirements, so that I can find the best candidate. | Low | 4 | 1. Use keyword matching/LLM API. 2. Explain why the match was recommended. | 8 | Optional AI feature (Bonus). | 2026-05-11 | 2026-05-18
US08 | Data Persistence | As a Developer, I want to store data in CSV/JSON, so that the system remains database-free. | High | 1-4 | 1. No SQL/NoSQL databases used. 2. Data survives app restart. | 3 | Compliance with Section 2.2. | 2026-03-06 | 2026-05-24